Monitoring

This is the regular collection of information while a project, programme or activity is being delivered. This information could include e.g. the number of sessions being delivered, how many people came to each session, which locations activities were delivered in, the number of downloads of a resource or views of an online video. Storing this information so it can be regularly reviewed will enable you to understand the delivery, reach and progress of your project.

What is monitoring, evaluation and learning?

Evaluation

Evaluation is the periodic process of bringing together various types of information (e.g. monitoring data, feedback surveys, consultation with staff) to examine whether your project, programme or activity is achieving its intended outcomes. This can help you to identify any areas where delivery is working well or any changes that are necessary to increase reach, effectiveness or impact.

Learning

Learning is the process of reflection and sense-making to support action and improvement. Learning may happen in various ways e.g. creating spaces for a staff team to reflect together, connecting with Camden residents, or engaging with similar organisations or wider stakeholders. Learning often involves considering the wider landscape e.g. what does the broader political or economic context mean for our project? Which potential partnerships could we develop? Who can we learn from to ensure that our activities are inclusive for all?

Why is MEL important?

A planned and proportionate approach to MEL can help with the following:

| Adaptation and ongoing improvement | Having the up-to-date information and spaces to regularly reflect on delivery will enable you to continuously adapt and improve, responding to ‘real-time’ feedback and other insights. |
| --- | --- |
| Telling your story and demonstrating your impact | Bringing together insights about the activities you’ve delivered, residents’ journeys and your learning can form a powerful story of your impact which can be shared with various audiences through engaging outputs. |
| Meeting funder requirements and applying for new funding | Funders may require you to report on funded activity and having robust evidence of your reach and impact can attract further funding. |
| Developing an evidence base to inform wider policy and practice | Establishing what works to support positive outcomes for Camden residents is beneficial for informing and influencing wider policy change and practice. |

Suggestions for data collection

It is very important to keep data collection proportionate and appropriate to your activities. Rocket Science will provide more detailed training in 2026 to help you to make some decisions about the level and types of data collection you will undertake. The following table provides some suggestions to prompt thinking on data collection:

| Data collection theme | Types of information you could collect |
| --- | --- |
| Activities delivered, resources provided and locations of delivery | - The quantity and type of activities, support or sessions that you have delivered - The quantity and type of resources that you have shared with residents - The locations in which activities have been delivered, including online |
| Target groups and reach | - Target groups for different activities - Total number of residents that have engaged with each activity - Demographic information about residents that have engaged with your project e.g. age, gender, ethnicity, housing location etc |
| Methods for outreach and communications | - The ways in which you have shared information about your project and undertaken outreach (e.g. publishing information in a local newsletter or attending community meetings to speak about your project) |
| Routes in and out of your organisation/project | - The ways in which people hear about or are signposted to your project (routes in) - Any additional types of support or activities they are signposted or referred to because of engaging with your project (routes out) |
| Sought change and changes for residents (outcomes) | - The positive changes for residents and communities that your project activities seek to support - The positive changes that your project has supported for residents and communities Note: data collection relating to outcomes could be open or categorised. For info - the sought outcomes of the wider We Make Camden programme relate to: - Access to a wide range of services and activities - Happiness - Improved health - Deeper sense of belonging - Increased connection to other residents - Opportunities to have a voice on issues that are important and to create change within the borough |
| Feedback, suggestions and learning | - Residents’ perspectives on your project including positives and suggestions for development - Lessons learned including reflections on any challenges faced and adaptations to delivery. |